## User story
Requirement ID | Issue Type | Summary | Priority
| Epic 1 | Ixigo Automation Testing | High
REQ_Ix_01 | Story 1 | Successful login with valid mobile number | High
REQ_Ix_01.1 | Sub story 1 | Given the user is on the login page | High
REQ_Ix_01.2 | Sub story 2 | User should be able to enter a valid mobile number | High
REQ_Ix_01.3 | Sub story 3 | User should authenticate successfully with correct OTP | High
REQ_Ix_01.4 | Sub story 4 | User should be redirected to booking page post login | High
REQ_Ix_02 | Story 2 | Unsuccessful login with invalid mobile number | High
REQ_Ix_02.1 | Sub story 1 | Given the user is on the login page | High
REQ_Ix_02.2 | Sub story 2 | System should reject login attempts with invalid mobile number | High
REQ_Ix_02.3 | Sub story 3 | System should prevent login if user clicks continue without valid input | High
REQ_Ix_02.4 | Sub story 4 | System should display error message. | High
REQ_Ix_03 | Story 3 | Search round_trip flights with Excel data | Medium
REQ_Ix_03.1 | Sub story 1 | Given the user is on the homepage | Medium
REQ_Ix_03.2 | Sub story 2 | Search for round-trip flights | Medium
REQ_Ix_03.3 | Sub story 3 | User should be able to enter departure location. | High
REQ_Ix_03.4 | Sub story 4 | User should be able to enter destination location. | High
REQ_Ix_03.5 | Sub story 5 | User sets travellers as "<adults>" adults, "<children>" children, "<infants>" infants and class as "<travel_class>" | High
REQ_Ix_03.6 | Sub story 6 | User clicks Search | High
REQ_Ix_03.7 | Sub story 7 | Search results should be displayed | High
REQ_Ix_04 | Story 4 | Filter flights by departure and arrival times | High
REQ_Ix_04.1 | Sub story 1 | User is on the selection page | High
REQ_Ix_04.2 | Sub story 2 | User clicks third filter departure as "<Departure>" | High
REQ_Ix_04.3 | Sub story 3 | User clicks fourth filter arrival as "<Arrival>" | High
REQ_Ix_04.4 | Sub story 4 | Select the first available flight | High
REQ_Ix_05 | Story 5 | Plan a trip | High
REQ_Ix_05.1 | Sub story 1 | User is on the ixigo homepage | Medium
REQ_Ix_05.2 | Sub story 2 | User clicks the Plan icon | Medium
REQ_Ix_05.3 | Sub story 3 | User clicks on Festivals | Medium
REQ_Ix_05.4 | Sub story 4 | Festivals page should open | Medium

## Test Scenario
TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No.of TestCases | Test Case Details
TS_01 | REQ_Ix_01 | Successful login with valid mobile number | Functional Testing | 4 | 1. Given the user is on the login page 2.When the user enters mobileno as "<Mobile_no>" 3. And enters the correct OTP 4.Then the user should be navigated to the booking page
TS_02 | REQ_Ix_02 | Unsuccessful login with invalid mobile number | Functional Testing | 4 | 1.Given the user is on the login page 2. When the user enters invalid mobileno as "<Mobile_No>" 3.And the user clicks the continue button 4.Then the system should display "<error_message>"
TS_03 | REQ_Ix_03 | Search round_trip flights with Excel data. | Functional Testing | 7 | 1. Given the user is on the homepage 2. When the user selects "Round Trip" trip type 3. And the user enters origin as "<from>" 4. And the user enters destination as "<to>" 5. And the user sets travellers as "<adults>" adults, "<children>" children, "<infants>" infants and class as "<travel_class>" 6. And the user clicks Search 7. Then search results should be displayed
TS_04 | REQ_Ix_04 | Filter flights by departure and arrival times. | Functional Testing | 4 | 1.Given the user is on the selection page 2.And the user clicks first filter departure as "<Departure>" 3.And the user clicks second filter arrival as "<Arrival>" 4.Then select the first available flight
TS_05 | REQ_Ix_05 | Plan a trip | Functional Testing | 4 | 1.Given the user is on the ixigo homepage 2.When the user clicks the Plan icon 3.And the user clicks on Festivals 4.Then the festivals page should open

## Test cases
Test case ID | Test Scenario ID | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual result Iteration 2 | Status Iteration 2 | Actual result Iteration 3 | Status Iteration 3 | Comments | Req reference
TS_01_TC_001 | TS_01 | Given the user is on the login page | Validate that the user is on the loginpage | 1. Launch browser. 2. Navigate to https://www.ixigo.com/. 3. Verify login page is displayed. | https://www.ixigo.com/ | Login page should be displayed with mobile number input field. | Login page displayed successfully. | Passed
TS_01_TC_002 | TS_01 | When the user enters mobileno as "<Mobile_no>" | Validate that the user has entered correct mobile number | 1. Enter a valid mobile number in the login page. 2. Click on “Continue”. | 8015993932 | System should accept the number and prompt for OTP. | Mobile number accepted and OTP is not displayed | Failed | Mobile number accepted and OTP is displayed | Passed |  |  |  | https://www.twilio.com/
TS_01_TC_003 | TS_01 | And enters the correct OTP | check the OTP entered properly | 1. Enter the correct OTP received on the registered number. 2. Click “Verify”. | OTP :xxxxxx | OTP should be accepted and user should be authenticated. | OTP accepted successfully. | Passed
TS_01_TC_004 | TS_01 | Then the user should be navigated to the booking page | Validate that user is on the booking page | 1. Complete login using valid mobile number and OTP. 2. Observe redirection. | Mobile: 8015993932 OTP: 123456 | User should be redirected to the booking/homepage. | User redirected to booking page successfully. | Passed
TS_02_TC_001 | TS_02 | Given the user is on the login page | Validate that the user is on the login page | 1. Launch browser. 2. Navigate to https://www.ixigo.com/. 3. Verify login page is displayed. | https://www.ixigo.com/ | Login page should be displayed with mobile number input field. | Login page displayed successfully. | Passed
TS_02_TC_002 | TS_02 | When the user enters invalid mobileno as "<Mobile_No>" | Validate system behavior when user enters an invalid mobile number | 1. Enter an invalid mobile number in the login page. 2. Click on “Continue”. | Mobile: 12345 (invalid format) Mobile: 9999999999 (unregistered) | System should reject the mobile number and display an error message. | System displayed error message correctly | Passed
TS_02_TC_003 | TS_02 | And the user clicks the continue button | Validate continue button action with invalid mobile number | 1. After entering an invalid mobile number, click “Continue”. | Mobile: 111222 (invalid) | System should not proceed to OTP screen, should stay on login page | System did not proceed and stayed on login page. | Passed
TS_02_TC_004 | TS_02 | Then the system should display "<error_message>" | Validate correct error message is displayed for invalid login attempt | 1. Enter invalid mobile number. 2. Click “Continue”. 3. Observe the error message displayed. | Mobile: 9999999999 Error Message: “Please enter a valid mobile number” | Correct error message should be shown to the user. | Error message “Please enter a valid mobile number” displayed successfully. | Passed
TS_03_TC_001 | TS_03 | Given the user is on the homepage | Validate that the homepage is displayed | 1. Launch browser. 2. Navigate to https://www.ixigo.com/. 3. Verify homepage is displayed. | URL: https://www.ixigo.com/ | Homepage should be displayed with trip type options. | Homepage displayed successfully. | Passed
TS_03_TC_002 | TS_03 | When the user selects "Round Trip" trip type | Validate round trip option selection | 1. On homepage, select “Round Trip” from trip type options. | Trip Type: Round Trip | Round Trip option should be selected. | Round Trip option selected successfully. | Passed
TS_03_TC_003 | TS_03 | And the user enters origin as "<from>" | Validate origin input functionality | 1. Enter origin city in “From” field. 2. Select from suggestions. | from excel | Origin should be set to Chennai | Origin selection failed – element could not be clicked due to an unexpected popup, leading to a TimeoutException. | Failed | Origin set successfully | Passed |  |  | By changing the wait duration and improving pop code it was handled.
TS_03_TC_004 | TS_03 | And the user enters destination as "<to>" | Validate destination input functionality | 1. Enter destination city in “To” field. 2. Select from suggestions. | from excel | Destination should be set to Mumbai. | Destination set successfully. | Passed | Destination selection failed – element could not be clicked due to an unexpected popup, leading to a TimeoutException. | Failed | Destination set successfully. | Passed | By changing the locator of the fields
TS_03_TC_005 | TS_03 | And the user sets travellers as "<adults>" adults, "<children>" children, "<infants>" infants and class as "<travel_class>" | Validate traveller count and class selection | 1. Open travellers and class selection. 2. Set travellers as per data. 3. Choose travel class. | Adults: 1 Children: 1 Infants: 0 Class: Economy | Travellers and class should be set successfully. | Travellers and class set successfully. | Passed
TS_03_TC_006 | TS_03 | And the user clicks Search | Validate search action | 1. Click the “Search” button after entering all details. | null | System should initiate flight search | Search initiated successfully. | Passed
TS_03_TC_007 | TS_03 | Then search results should be displayed | Validate that search results are shown | 1. Wait for search results page. 2. Verify flight options are listed. | From: Chennai To: Mumbai Trip Type: Round Trip | Flight search results should be displayed. | Flight search results displayed successfully. | Passed
TS_04_TC_001 | TS_04 | Given the user has search results displayed | Validate that flight search results are available before applying filters | 1. Launch browser and navigate to Ixigo. 2. Enter valid trip details (From, To, Date, Travellers, Class). 3. Click “Search”. 4. Verify search results page is displayed. | From: Chennai To: Mumbai Trip Type: Round trip Date: 20-Sep-2025 | Search results should be displayed with available flights. | Search results displayed successfully. | Passed
TS_04_TC_002 | TS_04 | When the user applies departure time filter | Validate departure time filter functionality | 1. In search results page, open filter section. 2. Select a departure time range (e.g., Morning 6AM–12PM). | Departure Time: 06:00–12:00 | Flights departing only in selected time range should be shown. | System displayed flights only in selected departure time range. | Passed
TS_04_TC_003 | TS_04 | And the user applies arrival time filter | Validate arrival time filter functionality | 1. In search results page, open filter section. 2. Select an arrival time range (e.g., Evening 6PM–12AM). | Arrival Time: 18:00–23:59 | Flights arriving only in selected time range should be shown. | System displayed flights only in selected arrival time range. | Passed
TS_04_TC_004 | TS_04 | Then filtered results should be displayed | Validate that only filtered flights are displayed | 1. Apply both departure and arrival filters. 2. Observe the results page. | Departure: 06:00–12:00 Arrival: 18:00–23:59 | Results should match both applied filters (departure + arrival). | Filtered results displayed correctly. | Passed
TS_05_TC_001 | TS_05 | Given the user is on the ixigo homepage | Validate that the user can navigate to homepage | 1. Launch browser and navigate to Ixigo. 2. Log in with valid mobile number and OTP. | URL: https://www.ixigo.com/ | Navigation should be done | Navigation done successfully. | Passed
TS_05_TC_002 | TS_05 | When the user clicks the Plan icon | Validate that the Plan icon works | 1. In the homepage, click on the "Plan" button. | Plan button | "Plan" button should be clicked | "Plan" button clicked successfully. | Passed
TS_05_TC_003 | TS_05 | And the user clicks on Festivals | Validate that the "Festivals" can be clicked on the Plan page | 1.In all options, click on the "Festivals" option. | Festivals option | "Festivals" option should be clicked | "Festivals" option clicked successfully | Passed
TS_05_TC_004 | TS_05 | Then the festivals page should open | Validate that the "Festivals" page opens | 1. Festivals page opens | Page opens | Festivals page should be opened | Festivals page opened successfully | Passed
8438xxxx55

## Defect report
Defect Id. | Module name | Defect Summary | Defect Priority | Assigned To | Status
DF_Ix_01 | Launching website | When an invalid URL such as https://www.ixgo.com/ is entered, the site redirects to a different landing page instead of displaying an error or a “Page Not Found” message | Low | xyz@gmail.com | Need to inform to the developers.
DF_Ix_02 | Authentication | The Login and Sign-Up options are not clearly distinguishable, leading to confusion for new users. | High | xyz@gmail.com | Need to inform to the developers.
DF_Ix_03 | Interface error | After logout, the user is not redirected to the Home Page; only the Ixigoer menu updates to show Login/Signup. | High | xyz@gmail.com | Need to inform to the developers.

## RTM
BR_ID | TS_ID | TC_ID | Status | DR_ID
BR_Ix_01 | TS_01 | TS_01_TC_001 | Pass | NA
|  | TS_01_TC_002 | Pass | NA
|  | TS_01_TC_003 | Pass | NA
|  | TS_01_TC_004 | Defect | DF_Ix_02
BR_Ix_02 | TS_02 | TS_02_TC_001 | Pass | NA
|  | TS_02_TC_002 | Pass | NA
|  | TS_02_TC_003 | Pass | NA
|  | TS_02_TC_004 | Pass | NA
BR_Ix_03 | TS_03 | TS_03_TC_001 | Pass | NA
|  | TS_03_TC_002 | Pass | NA
|  | TS_03_TC_003 | Pass | NA
|  | TS_03_TC_004 | Pass | NA
|  | TS_03_TC_005 | Pass | NA
|  | TS_03_TC_006 | Pass | NA
|  | TS_03_TC_007 | Pass | NA
BR_Ix_04 | TS_04 | TS_04_TC_001 | Pass | NA
|  | TS_04_TC_002 | Pass | NA
|  | TS_04_TC_003 | Pass | NA
|  | TS_04_TC_004 | Pass | NA
BR_Ix_05 | TS_05 | TS_05_TC_001 | Pass | NA
|  | TS_05_TC_002 | Pass | NA
|  | TS_05_TC_003 | Pass | NA
|  | TS_05_TC_004 | Pass | NA
|  | TS_05_TC_005 | Pass | NA
|  | TS_05_TC_006 | Pass | NA

## Summary
TEST EXECUTION SUMMARY
Project Name | Module Name | Total cases | Total Passed | Total Failed | Total Executed | Pass Percentage | Fail Percentage | Compilition Percentage
Ixigo Automation Testing | Successful Login | 4 | 4 | 0 | 4 | 100% | 0% | 100%
| Unsuccessful Login | 4 | 4 | 0 | 4 | 100% | 0% | 100%
| Searching Round_trip flights | 7 | 7 | 0 | 7 | 100% | 0% | 100%
| Applying filters | 4 | 4 | 0 | 4 | 100% | 0% | 100%
| Plan a trip | 4 | 4 | 0 | 4 | 100% | 0% | 100%